## Technical Development
Guru Vandan Technical Development Roadmap
| Version 0 | Version 1 | Version 2 | Version 3
Vx.0 | Flutter app base, Firebase setup, Android, web, and iOS project structure | Vx.0 — Modern iOS-aligned visual refresh with shorter, heading-led content | Events | Shop
Vx.1 | First launch language choice, Google sign-in, and phone OTP sign-in | Vx.1 — Light/dark mode switch and readable dark-mode footer navigation | Guru Gallery
Vx.2 | First-time profile setup with first, middle, and last name | Vx.2 — Daily Sacred Practice moved up, streak moved down, and first-timer streak corrected
Vx.3 | Spiritual home screen, first-name greeting, and welcome popup | Vx.3 — Maharshi Mehi Paramhans and Satsang Samigri terminology updates
Vx.4 | Offline morning satsang, evening satsang, and aarti audio | Vx.4 — Daily quote schedule, future queue, quote-of-the-day logic, and archive
Vx.5 | Meditation timer with presets, custom hours/minutes, Om, and ending chant | Vx.5 — Quote sharing, exact-quote deep links, and Android/iOS store fallback
Vx.6 | Meditation-only streak tracking with current, best, and total days | Vx.6 — Persistent quote likes and user engagement event tracking
Vx.7 | Dynamic bilingual wisdom quotes from admin with share option | Vx.7 — Browser admin portal with per-user timelines, combined statistics, and graphs
Vx.8 | More page with language switch, change name, coming soon modules, and logout | Vx.8 — Seek sliders for satsang and aarti playback
Vx.9 | Admin panel for quotes, editing, newest-first list, and user activity view | Vx.9 — Apple sign-in, provider linking, permanent account deletion, and session restore
Vx.10 | Release build: Android APK ready, web deployed, iOS files prepared | Vx.10 — Release 1.0.28 (31): meditation completion, lock-screen duration, and logout fixes

## Marketing
Guru Vandan Marketing Tracker
For date | Version | Marketing content
2026-08-15 | Version 1 | 3 reels
2026-08-15 | Version 1 | 2 posters
2026-08-15 | Version 1 | Instagram page

## Version 0 Details
Guru Vandan - Version 0 Feature Tracker
Everything listed here was completed or prepared in Version 0 of the Guruvandan app.
Version | Version 0 |  | Total items | 47
Status | Release-ready |  | Completed | 46
Last updated | 2026-08-12 |  | Prepared | 1
Category | Area | Feature | Status | Implementation notes | User benefit
Branding | App identity | Device app name shows Guru Vandan | Complete | Android, iOS, and web manifest naming updated. | Users see the correct devotional app name.
Branding | Logo | Guru Vandan logo applied | Complete | The shared Guru Vandan logo replaced the default Flutter icon. | The app feels official and recognizable.
Design | Theme | Spiritual crimson and off-white UI | Complete | Crimson, off-white, soft gold, and calm devotional styling used throughout. | The interface feels aligned with the spiritual school.
Design | Accessibility | Elder-friendly visual layout | Complete | Large text, simple actions, and spacious controls. | Older devotees can use the app with less confusion.
Language | First launch | Language selection before sign-in | Complete | User chooses English or Hindi before authentication. | The app starts in the user's preferred language.
Language | Settings | Language switch in More | Complete | Language can be changed later from the More page. | Users can switch language anytime.
Authentication | Google | Google sign-in | Complete | Google authentication flow added through Firebase. | Users can enter the app quickly with Google.
Authentication | Phone | Phone OTP sign-in | Complete | Phone number and OTP flow added. | Users without Google login can still sign in.
Authentication | Return users | Existing account handling | Complete | Known users are not asked for name again after login. | Repeat login feels smooth.
Profile | Onboarding | First-time name setup | Complete | First name, middle name, and last name captured separately. | Profiles are cleaner and easier to personalize.
Profile | Greeting | Home shows first name only | Complete | Greeting uses first name instead of full name. | The home screen feels personal without being crowded.
Profile | Edit name | Change name option in More | Complete | User can update name from the More page. | Wrong or changed names can be corrected.
Home | Welcome | Classy spiritual welcome popup | Complete | Shown after new user signup/name setup. | First entry feels warm and ceremonial.
Home | Navigation | Morning, Evening, and Dhyan quick buttons | Complete | Home cards navigate to their correct tabs/pages. | Main routines are reachable in one tap.
Home | Information | Collapsible About sections | Complete | About Guru Maharaj and About Guru Vandan content added. | Important context is present without overwhelming the home page.
Routine | Daily tracking | Routine completion tracking | Complete | Satsang, aarti, and meditation completion can be tracked. | Devotees can see their daily spiritual practice progress.
Satsang | Morning | Morning satsang audio bundled offline | Complete | Morning satsang audio is inside the APK assets. | No waiting for download before playback.
Satsang | Evening | Evening satsang audio bundled offline | Complete | Shaam satsang audio is inside the APK assets. | Evening satsang works directly from the app.
Satsang | Aarti | Aarti tab and audio | Complete | Separate Aarti tab added with bundled Aarti audio. | Aarti has its own clear place.
Satsang | Player | Audio progress and duration | Complete | Playback progress and total duration are shown. | Users understand where they are in the satsang.
Satsang | Completion | Complete button | Complete | User can mark satsang and aarti as complete. | Routine progress is explicit.
Audio | Silent mode | Silent phone popup before playback | Complete | Popup asks user to put phone on silent before satsang or meditation starts. | Practice begins with fewer distractions.
Audio | Background | Background playback and notification | Complete | Satsang, meditation, and Om continue when app is minimized. | Audio does not stop during practice.
Meditation | Preset timer | Preset meditation durations | Complete | 5, 10, 15, 20, 25, and 30 minute options. | Users can start common sessions quickly.
Meditation | Custom timer | Custom hours and minutes picker | Complete | Scrollable custom time picker added. | Longer or personal durations are supported.
Meditation | Controls | Start, pause, and reset | Complete | Timer control buttons added. | Users stay in control of the session.
Meditation | Ending chant | Chant plays only when timer ends | Complete | Opening chant was removed; closing chant plays after timed meditation. | Meditation time remains pure and uninterrupted.
Meditation | Om toggle | Om mantra background audio | Complete | Om audio can play endlessly when no meditation timer is running. | Users can listen for calm focus outside timer sessions.
Meditation | Om with timer | Om stops before final chant | Complete | If timer is running, Om stops before the closing chant plays. | Audio sequence remains clean.
Streak | Meditation streak | Meditation-only streak logic | Complete | Streak depends only on daily meditation continuity. | Users are encouraged to meditate daily.
Streak | Stats | Current, best, and total meditation days | Complete | Streak area explains continuity, not duration. | The meaning of the streak is easy to understand.
Wisdom | Dynamic quotes | Quotes fetched dynamically from Firebase | Complete | Wisdom page loads all admin-uploaded quotes when online. | New wisdom appears without rebuilding the app.
Wisdom | Newest first | Latest quote appears at top | Complete | Admin quotes are ordered newest first. | Fresh content is easy to find.
Wisdom | Bilingual | English and Hindi wisdom support | Complete | Quote language follows the selected app language. | Devotees get wisdom in their chosen language.
Wisdom | Sharing | Share button on each quote | Complete | Quote sharing includes the quote text and app link. | Users can share Sadguru wisdom through phone apps.
Wisdom | Library count | Wisdom page shows loaded quote count | Complete | Shows how many quotes are available. | Admin can verify content is reaching the app.
More | Modules | Shop, Events, Guru Gallery, and Jigyasa | Complete | Coming soon modules are placed inside More. | Future features are visible without cluttering core tabs.
More | Logout | Logout with confirmation | Complete | Logout returns user to the sign-in flow. | Shared devices can be signed out cleanly.
Admin | Separate URL | Admin page moved to separate route | Complete | Admin is accessed through the admin URL only. | Normal users do not see admin tools in More.
Admin | Quotes | Add bilingual wisdom quotes | Complete | Admin can enter English and Hindi quote text and attribution. | Spiritual content can be updated manually.
Admin | Edit | Edit existing wisdom quotes | Complete | Already uploaded quotes can be edited. | Mistakes can be corrected without database work.
Admin | Activity | User activity dashboard | Complete | Admin can view user activity in chart and text form. | Routine adoption can be monitored.
Backend | Firebase Auth | Authentication backend | Complete | Firebase Auth is used for Google and phone login. | The app has real account-based access.
Backend | Firebase Database | Realtime data storage | Complete | Users, quotes, routines, and activity are stored in Firebase Realtime Database. | Admin changes can appear dynamically in the app.
Build | Android | Release APK created | Complete | Latest Android APK is ready for install and sharing. | The app can be tested on Android devices.
Build | Web | GitHub Pages web app deployed | Complete | Live web app is deployed for browser review. | The work can be shared with the team instantly.
Build | iOS | iOS files prepared | Ready | iOS project files are ready for Mac or cloud compilation. | The next step can happen on Mac/cloud without rebuilding from scratch.

## Version 1 Details
Guru Vandan - Version 1 Feature Tracker
Completed work through Android release 1.0.28 (31), including the three latest reliability fixes.
Version | Version 1 |  | Total items | 35
Status | Ready for internal testing |  | Completed | 35
Last updated | 2026-09-20 |  | Open | 0
Category | Area | Feature | Status | Implementation notes | User benefit
Design | Visual system | iOS-aligned spiritual interface | Complete | Refreshed cards, typography, spacing, navigation, and devotional colors across the app. | A cleaner and more consistent experience on Android and iOS.
Design | Content | Explanation text removed | Complete | Long supporting copy was removed where a clear section heading already communicates the purpose. | Screens are easier to scan and feel less crowded.
Appearance | Theme | Light and dark mode switch | Complete | Users can change the visual theme from the app. | Comfortable viewing in bright and low-light settings.
Appearance | Dark mode | Readable footer navigation | Complete | Footer labels and icons use high-contrast colors in dark mode. | Every navigation label remains visible.
Home | Layout | Daily Sacred Practice moved above streak | Complete | The primary daily action appears before continuity statistics. | Users reach the daily routine faster.
Streak | First use | Yesterday streak hidden for first-time users | Complete | The previous-day indicator is omitted until the user has relevant history. | New users are not shown misleading streak data.
Content | Attribution | Maharshi Mehi Paramhans naming | Complete | Previous Sadguru Maharaj wording was replaced throughout relevant app sections. | Attribution is consistent with the approved name.
Content | Localization | Satsang Samigri Hindi label | Complete | The Hindi devotional-store wording was updated to Satsang Samigri. | The label matches the requested terminology.
Wisdom | Daily quote | One scheduled quote per day | Complete | Only the quote assigned to the current date is presented as the daily quote. | Users receive a focused daily teaching.
Wisdom | Queue | Future quote scheduling | Complete | Newly uploaded quotes fill upcoming dates in sequence. | Administrators can prepare many days of content in advance.
Wisdom | Archive | Previous daily quotes archive | Complete | Quotes move into the archive after their scheduled day. | Users can revisit earlier teachings.
Wisdom | Deep link | Open the exact shared quote | Complete | Shared links carry a quote identifier and route the installed app to that quote. | Recipients land directly on the intended teaching.
Wisdom | Store fallback | Android and iOS install fallback | Complete | Shared quote links provide Google Play and App Store destinations when the app is unavailable. | Recipients can install the correct app for their device.
Wisdom | Sharing | Guru Vandan share presentation | Complete | Quote sharing includes branded text, attribution, and a web/deep link. | Shared content is recognizable and actionable.
Wisdom | Engagement | Persistent quote likes | Complete | Quote likes are stored and included in analytics. | Popular teachings can be identified.
Audio | Satsang | Satsang seek slider | Complete | Users can drag the playback position backward or forward. | Listeners can repeat or skip to a chosen part.
Audio | Aarti | Aarti seek slider | Complete | Aarti playback supports direct position seeking. | Users have consistent controls across audio sections.
Analytics | App usage | App-open and screen-view tracking | Complete | Key navigation and app lifecycle events are recorded in Firebase. | The team can understand adoption and screen usage.
Analytics | Satsang | Listening-time tracking | Complete | Actual satsang and aarti playback time is recorded. | The admin portal can report real listening engagement.
Analytics | Meditation | Planned, actual, and completed time | Complete | Meditation starts, elapsed time, and successful completions are tracked. | The team can compare intent with completed practice.
Analytics | Wisdom | Quote views, shares, and likes | Complete | Wisdom interactions are captured as structured events. | The team can see which content users value.
Admin | Access | Browser admin portal | Complete | A responsive Firebase-hosted admin page is protected by administrator email/password authentication. | Authorized staff can manage the app from a phone or browser.
Admin | Users | Per-user activity timeline | Complete | The portal shows what each user did and when. | Support and engagement review can be user-specific.
Admin | Dashboard | Combined statistics and graphs | Complete | Aggregate totals, seven-day activity, and activity breakdowns are visualized. | Overall app usage is understandable at a glance.
Admin | Content | Quote management and scheduling | Complete | Administrators can add, edit, schedule, and review quote content. | Daily wisdom can be maintained without an app release.
Backend | Security | Admin-aware Firebase rules | Complete | Database access rules protect administration and user activity data. | Sensitive management functions remain restricted.
Privacy | Disclosure | Analytics privacy disclosure | Complete | The privacy page documents app activity collection and its operational purpose. | Users and reviewers receive clearer data-use information.
Authentication | Apple | Sign in with Apple | Complete | Apple authentication is integrated for supported devices. | iOS users have a platform-native login option.
Authentication | Linking | Provider conflict handling | Complete | Existing identities can be linked when the same account uses another provider. | Users avoid accidental duplicate accounts.
Account | Deletion | Permanent account deletion | Complete | Users can permanently delete their account and associated records, including provider revocation handling. | Account controls meet user and store expectations.
Authentication | Session | Silent session restoration | Complete | A valid Google/Firebase session is restored before showing sign-in after the app is closed. | Closing the app no longer signs the user out.
Meditation | Completion | Om meditation completes correctly | Complete | Timed Om playback now reaches the selected endpoint, plays the ending chant, and shows the completion message once. | Users receive the expected end-of-session confirmation.
Meditation | Lock screen | Correct timer duration in media controls | Complete | The media source presented to Android uses the selected meditation duration instead of the full Om recording length. | A one-minute session displays as one minute on the lock screen.
Release | Android | Signed Play Store app bundle | Complete | Version 1.0.28 with version code 31 was built, signed, and validated as an Android App Bundle. | The corrected build is ready for internal testing upload.
Quality | Verification | Static analysis, tests, and bundle validation | Complete | Flutter analysis passed, 27 automated tests passed, and the AAB manifest/signature were verified. | The release has repeatable technical checks before testing.
Need to be done - received for Version 1 and resolved in this build
Reported issue | Resolution | Status | Build | Verification / next check
Timed Om meditation did not play the ending chant or show the completion message. | Timed playback now ends at the selected duration and runs the normal completion flow. | Complete | 1.0.28 (31) | Automated tests and release build passed; confirm once on an internal-test device.
A one-minute meditation appeared as roughly three hours on the lock screen. | Android media metadata now exposes the selected timer duration instead of the source recording duration. | Complete | 1.0.28 (31) | AAB metadata/signature verified; confirm the media notification on a physical Android device.
Closing and reopening the app logged the user out. | The app silently restores a valid Google/Firebase session before showing the sign-in screen. | Complete | 1.0.28 (31) | Authentication flow compiles and tests pass; confirm session persistence through internal testing.